## Estimation Template
Late Joiners
Tips +
Tasks | Sarah | Luke | Matthew | Tyrone | Blair | Shae | Average
User Accounts | 18 | 24 | 30 | 30 | 43 | 25 | 28.3333
Tournament/Match data storage | 8 | 10 | 15 | 12 | 7 | 10 | 10.3333
Tournament/Match display | 45 | 40 | 40 | 40 | 49 | 35 | 41.5
Allow selection of picks/store picks | 15 | 16 | 10 | 12 | 32 | 15 | 16.6667
Display results/user record | 25 | 30 | 30 | 32 | 32 | 35 | 30.6667
Source data from APIs | 32 | 40 | 30 | 30 | 40 | 30 | 33.6667
Allow result crowd-sourcing | 28 | 24 | 25 | 24 | 39 | 20 | 26.6667
Automatic backups | 5 | 1 | 10 | 1 | 11 | 5 | 5.5
4640:00
Task descriptions:
User Accounts | Our system should be able to store information about user accounts, and allow users to create new accounts or delete their currently existing account
Tournament/Match data storage | Our system should be capable of storing information on various soccer tournaments in a mongoDB instance.
Tournament/Match display | Our system should be able to display information on overall tournaments as well as individual matches to the user
Allow selection of picks/store picks | Our system should allow the user to nominate their picks for the currently chosen match (whether simply picking who they think will win or the final score), with this data then being saved in the database.
Display results/user record | Our system should display to users the actual results for games that have concluded where that user had a pick, as well as data about their overall picking record.
Source data from APIs | Our system should source tournament and game data in real-time from APIs for tournaments where an API is available.
Allow result crowd-sourcing | The system should have the ability to 'crowd-source' result information. i.e. Users can enter the score for a game and once a threshold of submitted results have been submitted, the results for the game will be updated and players scored on their picks
Automatic backups | Our system should have a suitable schedule and process for automatic backups of the database. This can be integrated as part of the Heroku platform we plan to deploy on.

## Justifications
Blair |  | Luke
(For the sake of simplicity, all research items include all research required for that specific feature, even if some of that research would already have been completed by a team member for another feature (i.e. order of features/specific team members working on each do not need to be taken into consideration)
1. User accounts |  | 1. User accounts
(Our system should be able to store information about user accounts, and allow users to create new accounts or delete their currently existing account) |  | Adding JWT token support to API | 8
Research (all relevant learning) | 12 | Creating user model | 2
MongoDB collection design and creation | 4 | Creating claims check middleware for express api | 6
Frontend design/angular template creation | 7 | User login/register UI | 8
Angular typescript component | 7
Nodejs/express Backend code | 8
Integration testing/debugging | 5
TOTAL | 43 |  | 24
2. Tournament/Match data storage |  | 2. Tournament/Match data storage
(Our system should be capable of storing information on various soccer tournaments in a mongoDB instance)
Research (all relevant learning) | 3 | Create tournament model | 5
MongoDB collection design and creation | 4 | Create tournament repository | 5
TOTAL | 7
10
3. Tournament/Match display |  | 3. Tournament/Match display
(Our system should be able to display information on overall tournaments as well as individual matches to the user)
Research (all relevant learning) | 12 | Implement front end UI | 16
Frontend design/angular template creation | 10 | Create resuable styled components | 8
Angular typescript component | 10 | Fetch data from API | 8
Nodejs/express Backend code | 9 | Persist data back to API | 8
Integration testing/debugging | 8
TOTAL | 49 |  | 40
4. Allow selection of picks/store picks |  | 4. Allow selection of picks/store picks
(Our system should allow the user to nominate their picks for the currently chosen match (whether simply picking who they think will win or the final score), with this data then being saved in the database)
Research (all relevant learning) | 12 | Displaying of required picks for user | 8
MongoDB collection design and creation | 5 | UI to select picks | 8
Frontend design/angular template alteration (altering existing match display template to add UI elements allowing user to select their picks) | 4 | Storing of picks via API | 5
Angular typescript component | 3 | Fetching required picks from API | 8
Nodejs/express Backend code | 4 | Creating model hooks | 5
Integration testing/debugging | 4 | Authentication and authorisation of picks | 6
TOTAL | 32 |  | 40
5. Display results/user record |  | 5. Display results/user record
(Our system should display to users the actual results for games that have concluded where that user had a pick, as well as data about their overall picking record)
Research (all relevant learning) | 9 | User leaderboard screen | 10
Frontend design/angular template creation | 7 | User results screen | 15
Angular typescript component | 5 | Pull data from API | 5
Nodejs/express Backend code | 6
Integration testing/debugging | 5
TOTAL | 32 |  | 30
E1. Source data from APIs |  | E1. Source data from APIs
(Our system should source tournament and game data in real-time from APIs for tournaments where an API is available)
Research (Find APIs, investigate hosting environment options) | 6 | Find compatible APIs | 6
Develop backend component to retrieve data from APIs and insert/update match results in mongoDB | 12 | Create API services | 6
Develop backend component to retrieve tournament data from APIs and insert into mongoDB | 12 | Create microservice to pull score data from APIs | 16
Perform required backend/hosting environment configuration to ensure backend component is executed on a regular schedule | 2 | Storing scores back via API | 4
Testing and debugging | 8 | Create microservice instance on Heroku for all environments | 8
TOTAL | 40 |  | 40
E2. Allow result crowd-sourcing |  | E2. Allow result crowd-sourcing
(The system should have the ability to 'crowd-source' result information. i.e. Users can enter the score for a game and once a threshold of submitted results have been submitted, the results for the game will be updated and players scored on their picks)
Research (all relevant learning) | 15 | Create server-side model hook to determine if threshold met | 8
Develop backend component to determine if threshold has been reached and update match results accordingly | 7 | Front end score selection modal | 8
Frontend design/angular template alteration (altering existing match display template to add UI elements allowing user to report the match score) | 5 | Store crowd scores via API | 8
Angular typescript component | 3
Nodejs/express Backend code | 3
Integration testing/debugging | 6
TOTAL | 39 |  | 24
E3. Automatic backups |  | E3. Automatic backups
(Our system should have a suitable schedule and process for automatic backups of the database. This can be integrated as part of the Heroku platform we plan to deploy on)
Research (all relevant learning) | 4 | Configure Mlab to backup the data | 1
Provision and configuration of relevant storage | 1
Develop backend component to backup data from database to storage | 3
Perform required backend/hosting environment configuration to ensure backend component is executed on a regular schedule | 1
Testing and debugging | 2
TOTAL | 11 |  | 1