## Estimation Template
Late Joiners
Tips +
Tasks | Sarah | Luke | Matthew | Tyrone | Blair | Shae | Average
User Accounts | 18 | 24 | 30 | 30 | 43 | 25 | 28.3333
Tournament/Match data storage | 8 | 10 | 15 | 12 | 7 | 10 | 10.3333
Tournament/Match display | 45 | 40 | 40 | 40 | 49 | 35 | 41.5
Allow selection of picks/store picks | 15 | 16 | 10 | 12 | 32 | 15 | 16.6667
Display results/user record | 25 | 30 | 30 | 32 | 32 | 35 | 30.6667
Source data from APIs | 32 | 40 | 30 | 30 | 40 | 30 | 33.6667
Allow result crowd-sourcing | 28 | 24 | 25 | 24 | 39 | 20 | 26.6667
Automatic backups | 5 | 1 | 10 | 1 | 11 | 5 | 5.5
4640:00
Task descriptions:
User Accounts | Our system should be able to store information about user accounts, and allow users to create new accounts or delete their currently existing account
Tournament/Match data storage | Our system should be capable of storing information on various soccer tournaments in a mongoDB instance.
Tournament/Match display | Our system should be able to display information on overall tournaments as well as individual matches to the user
Allow selection of picks/store picks | Our system should allow the user to nominate their picks for the currently chosen match (whether simply picking who they think will win or the final score), with this data then being saved in the database.
Display results/user record | Our system should display to users the actual results for games that have concluded where that user had a pick, as well as data about their overall picking record.
Source data from APIs | Our system should source tournament and game data in real-time from APIs for tournaments where an API is available.
Allow result crowd-sourcing | The system should have the ability to 'crowd-source' result information. i.e. Users can enter the score for a game and once a threshold of submitted results have been submitted, the results for the game will be updated and players scored on their picks
Automatic backups | Our system should have a suitable schedule and process for automatic backups of the database. This can be integrated as part of the Heroku platform we plan to deploy on.

## Justifications
Blair |  | Luke |  | Matt
(For the sake of simplicity, all research items include all research required for that specific feature, even if some of that research would already have been completed by a team member for another feature (i.e. order of features/specific team members working on each do not need to be taken into consideration)
1. User accounts |  | 1. User accounts |  | 1. User accounts
(Our system should be able to store information about user accounts, and allow users to create new accounts or delete their currently existing account) |  | Adding JWT token support to API | 8 | Research best approach/tutorials | 10
Research (all relevant learning) | 12 | Creating user model | 2 | User Entry Component Template Design | 5
MongoDB collection design and creation | 4 | Creating claims check middleware for express api | 6 | User Entry Component Template Coding | 5
Frontend design/angular template creation | 7 | User login/register UI | 8 | User model creation | 5
Angular typescript component | 7 |  |  | Testing | 5
Nodejs/express Backend code | 8
Integration testing/debugging | 5
TOTAL | 43 |  | 24 |  | 30
2. Tournament/Match data storage |  | 2. Tournament/Match data storage |  | 2. Tournament/Match data storage
(Our system should be capable of storing information on various soccer tournaments in a mongoDB instance)
Research (all relevant learning) | 3 | Create tournament model | 5 | Tournament Model design | 5
MongoDB collection design and creation | 4 | Create tournament repository | 5 | DB creation and implementation | 5
TOTAL | 7 |  |  | Testing | 5
|  |  | 10 |  | 15
3. Tournament/Match display |  | 3. Tournament/Match display |  | 3. Tournament/Match display
(Our system should be able to display information on overall tournaments as well as individual matches to the user)
Research (all relevant learning) | 12 | Implement front end UI | 16 | Bootstrap Page Design (incl. responsive) | 20
Frontend design/angular template creation | 10 | Create resuable styled components | 8 | Source Graphics | 5
Angular typescript component | 10 | Fetch data from API | 8 | Adapt design to Angular component template | 5
Nodejs/express Backend code | 9 | Persist data back to API | 8 | Implement Controllers/Services etc. | 5
Integration testing/debugging | 8 |  |  | Testing | 5
TOTAL | 49 |  | 40 |  | 40
4. Allow selection of picks/store picks |  | 4. Allow selection of picks/store picks |  | 4. Allow selection of picks/store picks
(Our system should allow the user to nominate their picks for the currently chosen match (whether simply picking who they think will win or the final score), with this data then being saved in the database)
Research (all relevant learning) | 12 | Displaying of required picks for user | 8 | Gather data from form submission | 4
MongoDB collection design and creation | 5 | UI to select picks | 8 | Write to DB | 4
Frontend design/angular template alteration (altering existing match display template to add UI elements allowing user to select their picks) | 4 | Storing of picks via API | 5 | Testing | 2
Angular typescript component | 3 | Fetching required picks from API | 8
Nodejs/express Backend code | 4 | Creating model hooks | 5
Integration testing/debugging | 4 | Authentication and authorisation of picks | 6
TOTAL | 32 |  | 40 |  | 10
5. Display results/user record |  | 5. Display results/user record |  | 5. Display results/user record
(Our system should display to users the actual results for games that have concluded where that user had a pick, as well as data about their overall picking record)
Research (all relevant learning) | 9 | User leaderboard screen | 10 | Bootstrap Design of view (incl responsiveness) | 10
Frontend design/angular template creation | 7 | User results screen | 15 | Adapt design to component template | 5
Angular typescript component | 5 | Pull data from API | 5 | Implement controller/services for display (incl. authentication) | 10
Nodejs/express Backend code | 6 |  |  | Testinng | 5
Integration testing/debugging | 5
TOTAL | 32 |  | 30 |  | 30
E1. Source data from APIs |  | E1. Source data from APIs |  | E1. Source data from APIs
(Our system should source tournament and game data in real-time from APIs for tournaments where an API is available)
Research (Find APIs, investigate hosting environment options) | 6 | Find compatible APIs | 6 | Research available API's | 5
Develop backend component to retrieve data from APIs and insert/update match results in mongoDB | 12 | Create API services | 6 | Register with API services (register key etc.) | 2
Develop backend component to retrieve tournament data from APIs and insert into mongoDB | 12 | Create microservice to pull score data from APIs | 16 | Implement backend retrievel of API data | 10
Perform required backend/hosting environment configuration to ensure backend component is executed on a regular schedule | 2 | Storing scores back via API | 4 | Implement parser to parse data into relevant models in DB | 10
Testing and debugging | 8 | Create microservice instance on Heroku for all environments | 8 | Testing | 3
TOTAL | 40 |  | 40 |  | 30
E2. Allow result crowd-sourcing |  | E2. Allow result crowd-sourcing |  | E2. Allow result crowd-sourcing
(The system should have the ability to 'crowd-source' result information. i.e. Users can enter the score for a game and once a threshold of submitted results have been submitted, the results for the game will be updated and players scored on their picks)
Research (all relevant learning) | 15 | Create server-side model hook to determine if threshold met | 8 | Research algorithmic approach to data collection | 5
Develop backend component to determine if threshold has been reached and update match results accordingly | 7 | Front end score selection modal | 8 | Develop system to parse exsiting data to validate | 10
Frontend design/angular template alteration (altering existing match display template to add UI elements allowing user to report the match score) | 5 | Store crowd scores via API | 8 | Develop controller to display sourced data in view | 3
Angular typescript component | 3 |  |  | Modify template to allow display of information | 2
Nodejs/express Backend code | 3 |  |  | Testing | 5
Integration testing/debugging | 6
TOTAL | 39 |  | 24 |  | 25
E3. Automatic backups |  | E3. Automatic backups |  | E3. Automatic backups
(Our system should have a suitable schedule and process for automatic backups of the database. This can be integrated as part of the Heroku platform we plan to deploy on)
Research (all relevant learning) | 4 | Configure Mlab to backup the data | 1 | Research in-system backup options | 3
Provision and configuration of relevant storage | 1 |  |  | Implement backup schedule | 3
Develop backend component to backup data from database to storage | 3 |  |  | Testing (incl. sample DR event) | 4
Perform required backend/hosting environment configuration to ensure backend component is executed on a regular schedule | 1
Testing and debugging | 2
TOTAL | 11 |  | 1 |  | 10