## Student 1
LateJoiners
Code Repository: https://github.com/LateJoiners/code
Documents Repository: https://github.com/LateJoiners/docs
Frontend Hosting: https://dev-late-joiners.netlify.com/
Student Number |  | Full Enrolled Name
s3655740 |  | Shae Tatlock
Week 1-4 (28th May 2018 - 24th June 2018)
Task | Type (Project or Coursework) | Supporting Documentation | Hours spent
Watch video chats, make relevant notes | Coursework |  | 3
Watch mentor meeting | Coursework |  | 0.5
Group meeting | Coursework |  | 2
Contribute to Assignment 1 (Personal Bio, some work towards features.) Joined late so much was done. | Project | https://github.com/LateJoiners/docs/commit/606151b3ced6cb4a669472e5190c9d28efe901c2 | 3
Completed markdown tutorial | Project |  | 1.5
Total Hours: |  |  | 10
Week 5 (25th June 2018 – 1st July 2018)
Task | Type (Project or Coursework) | Supporting Documentation | Hours spent
Watch video chats, make notes | Coursework |  | 1
Watched mentor meeting | Coursework |  | 0.5
Group meeting | Coursework |  | 0.5
Started angular tutorial | Project | https://trello.com/c/VBvodFEy/97-start-working-on-official-angular-tutorial | 3
Completed code acadamy html/css | Project |  | 3
8
Week 6 (2nd July 2018 - 8th July 2018)
Task | Type (Project or Coursework) | Supporting Documentation | Hours spent
Watch video chats, make relevant notes | Coursework |  | 1
Watch mentor meeting | Coursework |  | 0.5
Group meeting | Coursework |  | 0.5
Countinue angular tutorial | Project | https://trello.com/c/T73XpCHL/131-continue-working-on-official-angular-tutorial | 4
Code Acadamy making a website | Project | https://trello.com/c/SLWeaOW0/1-tools-resources | 3
Total Hours: |  |  | 9
Week 7 (9th July 2018 - 15th July 2018)
Task | Type (Project or Coursework) | Supporting Documentation | Hours spent
Watch video chats, make relevant notes | Coursework |  | 1
Watch mentor meeting | Coursework |  | 0.5
Group meeting | Coursework |  | 1
Finish angular tutorial | Project | https://trello.com/c/mcKUmMWh | 4
Started research for CSS design references | Project | https://github.com/LateJoiners/docs/commit/d1f2c51ecfdf35aa1a9471b8ba373ff47e636740 | 1
Assignment 2 prototyping | Project | https://trello.com/c/OXwAuVyB/115-research-prototyping-software | 1.5
Started on Assignment 2 | Project | https://trello.com/c/v4crUofR | 1
Total Hours: |  |  | 10
Week 8 (16th July 2018 - 22nd July 2018)
Task | Type (Project or Coursework) | Supporting Documentation | Hours spent
Watch video chats, make relevant notes | Coursework |  | 1
Watch mentor meeting | Coursework |  | 0.5
Group meeting | Coursework |  | 0.5
Finished design refrences | Project | https://github.com/LateJoiners/docs/commit/d1f2c51ecfdf35aa1a9471b8ba373ff47e636740 | 1
Estimations and Justifications for Assignment 2 | Coursework | Submitted | 0.5
Mock up and prototype completed | Project | https://github.com/LateJoiners/docs/commit/2bd43450c151278dcb734c319ad669c40bfea9d4 | 5
Total Hours: |  |  | 8.5
Week 9 (23rd July 2018 - 29th July 2018)
Task | Type (Project or Coursework) | Supporting Documentation | Hours spent
Watch video chats, make relevant notes | Coursework |  | 1
Watch mentor meeting | Coursework |  | 0.5
Group meeting | Coursework |  | 1
further prototyping | Project | https://github.com/LateJoiners/docs/commit/2bd43450c151278dcb734c319ad669c40bfea9d4 | 2
Team Evaluation 1 | Coursework |  | 3
Total Hours: |  |  | 7.5
Week 10 (30th July 2018 - 5th August 2018)
Task | Type (Project or Coursework) | Supporting Documentation | Hours spent
Watch video chats, make relevant notes | Coursework |  | 1
Watch mentor meeting | Coursework |  | 0.5
General research for Assignment 3 | Project |  | 4
New Job and sickness | External factor
Total Hours: |  |  | 5.5
Week 11 (6th August 2018 – 12th August 2018)
Task | Type (Project or Coursework) | Supporting Documentation | Hours spent
Watch video chats, make relevant notes | Coursework |  | 1
Watch mentor meeting | Coursework |  | 0.5
Group meeting | Coursework |  | 1
Started work on assignment 3 | Project |  | 2
End of Illness | External factor
Total Hours: |  |  | 4.5
Week 12 (13th August 2018 - 19th August 2018)
Task | Type (Project or Coursework) | Supporting Documentation | Hours spent
Watch video chats, make relevant notes | Coursework |  | 1
Watch mentor meeting | Coursework |  | 0.5
Group meeting | Coursework |  | 1
Assignment 3 (Creating new navbar and troubleshooting) | Project | https://github.com/LateJoiners/code/commit/d357f0e3ef64b4ab8aa7065f117d04321a316201 (Finished product after trouble shooting) | 4
Complete Matt’s google forms survey to provide material for Assignment 3 (Took longer than expected from documents not going through) | Coursework | https://docs.google.com/forms/d/e/1FAIpQLSenvE6PFhfXXanPCWFthhG8gJbLat5abV9Oplr2Uf0Jq_G_gQ/viewform?usp=sf_link | 1.5
Angular refresher | Project |  | 1
Total Hours: |  |  | 9
Week 13 (20th August 2018 - 26th August 2018)
Task | Type (Project or Coursework) | Support Documentation | Hours spent
Complete teamlog | Coursework | Look at this exel | 1
Watch mentor meeting | Coursework |  | 0.5
Help Complete assignment 3 part 2 (Spent more time than 15 hours, most of it was making sure the navbar worked correctly, was an easy fix most of the time spent on troubleshooting) | Project | https://github.com/LateJoiners/code/commit/597182329ae4c13cd0b592cfebfc150a04084cb0 (Public and private Slack messages also can confirm) | 15
Uploaded navbar (finished troubleshooting. Didn’t have the right scripts in the html) | Project | https://github.com/LateJoiners/code/commit/d357f0e3ef64b4ab8aa7065f117d04321a316201 | 1
Total Hours: |  |  | 17.5
Total Study Period Coursework Hours: | 20 | Total Study Period Project Hours: | 60
Total Study Period Hours: |  |  | 80