## Blair
LateJoiners
Code Repository: https://github.com/LateJoiners/code
Documents Repository: https://github.com/LateJoiners/docs
Frontend Hosting: https://dev-late-joiners.netlify.com/
Student Number |  | Full Enrolled Name
s3641830 |  | Blair David Fraser
Week 1-4 (28th May 2018 - 24th June 2018)
Task | Type | Supporting Documentation | Hours
Watch video chats, make relevant notes | Coursework |  | 3
Mentor meeting | Coursework |  | 0.5
Group Meeting | Coursework |  | 0.5
Get up to speed with Git enough to contribute to assignment 1 (watch Lynda videos, practise) | Project | https://trello.com/c/ZCnaGG8U/85-get-up-to-speed-on-git-commandline-basics | 3
Contribute to Assignment 1 (Personal Bio, some work towards features (and validation), risks, timeline (personal and team) and trello cards) | Project | https://github.com/LateJoiners/docs/commit/f93d3b9fa6e9694c1ed29aea92700e42d97e355c https://github.com/LateJoiners/docs/commit/830c74bb753f6cdcf641216014ff535840794291 https://github.com/LateJoiners/docs/commit/51868081bd8370f5078b1b4d92e99a1e0e071196 https://github.com/LateJoiners/docs/commit/04da7ea6a08d4a9f67c275665d9e90f950feb230 https://github.com/LateJoiners/docs/commit/7a0f769644fa2a8cd6d7f53e509c939bce6d4758 https://github.com/LateJoiners/docs/commit/83b017e9a5be211c26b7f0fd80f8ead693f5c53a | 12
Initial research on tutorials | Project | https://trello.com/c/SLWeaOW0/1-tools-resources | 3
Complete markdown tutorial | Project | https://trello.com/c/Nl8Wuy7k/98-complete-markdown-tutorial | 1
Start working through angular tutorial | Project | https://trello.com/c/VBvodFEy/97-start-working-on-official-angular-tutorial | 1
Total Hours: |  |  | 24
Week 5 (25th June 2018 – 1st July 2018)
Task | Type | Supporting Documentation | Hours
Watch video chat, make relevant notes | Coursework |  | 1
Mentor meeting | Coursework |  | 0.5
Group Meeting | Coursework | https://github.com/LateJoiners/docs/commit/123938f313cf8564976d62395f023e37f6b1d653 | 0.5
Continue working on angular tutorial | Project | https://trello.com/c/T73XpCHL/131-continue-working-on-official-angular-tutorial | 6
Investigate bootstrap tutorials/documentation, methods for integrating bootstrap and our other tools (i.e. angular) | Project | https://trello.com/c/ZmpI8BiM/104-determine-if-some-knowledge-is-required-of-any-other-frameworks-ie-bootstrap-and-if-so-formulate-plan-to-attain-it | 2
Research MongoDB by reading documentation (incl setup of simple schema, practise simple operations) | Project | https://trello.com/c/zevU1ayZ/103-start-mongodb-learning | 3
Total Hours: |  |  | 13
Week 6 (2nd July 2018 - 8th July 2018)
Task | Type | Supporting Documentation | Hours
Watch video chat, make relevant notes | Coursework |  | 1
Mentor meeting | Coursework |  | 0.5
Research tools for development of mockups for assignment 2 | Project | Referenced in slack channel (general) on 11/7/18 Tools investigated but ultimately not used: Layoutit.com Buildbootstrap.com Wireframesketcher.com Proto.io Dia (Pingendo ultimately chosen) | 4
More MongoDB research/practise | Project | https://trello.com/c/Fd15PYlj/105-complete-mongodb-learning | 2
Complete angular tutorial | Project | https://trello.com/c/wRwx59ap/102-complete-work-on-official-angular-tutorial | 2
Research integration of stack elements | Project | https://trello.com/c/4LjyC7UG/108-find-and-start-working-on-mean-whole-stack-tutorial | 1
Familiarize self with bootstrap | Project | https://trello.com/c/C2SVjqdr/116-get-some-basic-practise-working-with-bootstrap-components-along-with-angular | 1
Total Hours: |  |  | 11.5
Week 7 (9th July 2018 - 15th July 2018)
Task | Type | Supporting Documentation | Hours
Watch video chat, make relevant notes | Coursework |  | 1
Mentor meeting | Coursework |  | 0.5
Group Meeting | Coursework |  | 0.5
Familiarize self with Pingendo (GUI tool we used to create mockup screens w/ bootstrap) | Project |  | 2
Create initial login mockup screen | Project | https://github.com/LateJoiners/docs/commit/0cf95aa9b9622489d17af4c3af82588731bac8c9 | 3
Complete initial peer feedback | Coursework | https://trello.com/c/mXZhi4JC/119-complete-peer-feedback-1 https://github.com/LateJoiners/docs/commit/6dd662f02a6fa8cc0094a3b4a69e939540000ee2 https://github.com/LateJoiners/docs/commit/c67ce0d9f9d74f8c275ad6ec896f0a319927c6aa | 5
Total Hours: |  |  | 12
Week 8 (16th July 2018 - 22nd July 2018)
Task | Type | Supporting Documentation | Hours
Watch video chat, make relevant notes | Coursework |  | 1
Group Meeting | Coursework |  | 1
Second Group Meeting | Coursework |  | 1
Create login screen error conditions mockup | Project | https://github.com/LateJoiners/docs/commit/2c6f866d758b3c2b4dc9a697c3fd043bb8a53864 | 1
Create account sign up screen mockup (incl error conditions) | Project | https://trello.com/c/i4htOHDH/5-assignment-2-submission | 3
Create account details screen mockup (incl error conditions) | Project | https://github.com/LateJoiners/docs/commit/5ca700f0cae764cd1b5a3edacce2b43909f4ce94 | 2
Complete estimations and justifications | Coursework | https://trello.com/c/i4htOHDH/5-assignment-2-submission | 2
Collate assignment PDF and submit | Coursework | https://github.com/LateJoiners/docs/commit/1dd2cbadd5479df394c4e87dd3a5d5ffc54a0dbe | 5
Collate estimations and submit | Coursework | https://github.com/LateJoiners/docs/commit/b28be3a6dff418d7ad685725ffe00fe900c60390 | 2
Total Hours: |  |  | 18
Week 9 (23rd July 2018 - 29th July 2018)
Task | Type | Supporting Documentation | Hours
Watch video chat, make relevant notes | Coursework |  | 1
Team Evaluation 1 | Coursework |  | 3
Group Meeting | Coursework |  | 0.5
Total Hours: |  |  | 4.5
Week 10 (30th July 2018 - 5th August 2018)
Task | Type | Supporting Documentation | Hours
Watch video chat, make relevant notes | Coursework |  | 1
Group Meeting | Coursework |  | 1
Moving house this week – time available for course very limited | External factor |  | --
Total Hours: |  |  | 2
Week 11 (6th August 2018 – 12th August 2018)
Task | Type | Supporting Documentation | Hours
Watch video chat, make relevant notes | Coursework |  | 1
Complete Peer Feedback 2 | Coursework | https://trello.com/c/S0kD3UBD/130-complete-peer-feedback-2 | 4
Wrangle with issues with local development Environment | Project | Referenced on slack (private messages to Luke, Thursday 16th – yes I *really* should have asked for help before then) | 3
Total Hours: |  |  | 8
Week 12 (13th August 2018 - 19th August 2018)
Task | Type | Supporting Documentation | Hours
Watch video chat, make relevant notes | Coursework |  | 1
Complete Matt’s google forms survey to provide material for Assignment 3 | Coursework | https://docs.google.com/forms/d/e/1FAIpQLSenvE6PFhfXXanPCWFthhG8gJbLat5abV9Oplr2Uf0Jq_G_gQ/viewform?usp=sf_link | 3
Wrangle further with issues with local development Environment | Project | Referenced on slack (private messages to Luke, Thursday 16th) | 1
Refresh angular knowledge | Project |  | 2
Templatize login screen | Project | https://github.com/LateJoiners/code/commit/311184599bb385a9e86701f9f9593d9a0ec85e9e | 2
Start work on templatizing account details screen | Project | Ultimately commited as https://github.com/LateJoiners/code/commit/2787836cb990cef9fece761da946fae33ee37b12 | 2
Review Assignment 3 Part 1 document in response to Matt’s request for feedback (ultimately could only conclude that Matt and Tyrone did a fantastic job – sadly only feedback I could provide was saying that I could not think of anything to add to it) | Project |  | 1
Total Hours: |  |  | 12
Week 13 (20th August 2018 - 26th August 2018)
Task | Type | Supporting Documentation | Hours
Complete this document | Coursework | You’re looking at it | 2
Mentor meeting | Coursework |  | 0.5
Complete templatization of accounts screen | Project | https://github.com/LateJoiners/code/commit/2787836cb990cef9fece761da946fae33ee37b12 | 1
Results page (templatized, created service, created API endpoints (serving mock data only) – incl CSS division of team logos images (duplication of effort, sadly), getting up to speed on setting up express endpoints) | Project | https://github.com/LateJoiners/code/commit/5d743c91c929351fe86a01c1025c03ddd99c0763 https://github.com/LateJoiners/code/commit/4c620f4fd670da3ffc7d6cb04f1d0e6e3726a876 | 10
Total Hours: |  |  | 13.5
Total Study Period Coursework Hours: | 44.5 | Total Study Period Project Hours: | 74
Total Study Period Hours: |  |  | 118.5

## Student 1
LateJoiners
Code Repository: https://github.com/LateJoiners/code
Documents Repository: https://github.com/LateJoiners/docs
Frontend Hosting: https://dev-late-joiners.netlify.com/
Student Number |  | Full Enrolled Name
s3439728 |  | Matt Greig
Week 1-4 (28th May 2018 - 24th June 2018)
Task | Type (Project or Coursework) | Supporting Documentation | Hours spent
Watch video chats, make relevant notes | Coursework
Mentor meeting | Coursework |  | 0.5
Group Meeting | Coursework |  | 0.5
Assignment 1 Bio section | Coursework | https://github.com/LateJoiners/docs/commit/835481a3749d3c8ef67fa1360b509ed5b876760a
Assignment 1 Communications section | Coursework | https://github.com/LateJoiners/docs/commit/a3e7ccc24e4023b167cc00e5e068695a0fd7d600
Create tasks and associated trello cards | Coursework
Finalize assignment 1 | Coursework | https://github.com/LateJoiners/docs/commit/616bd50fedc6d1540916e104b01d861148d26311 https://trello.com/c/KzSC4xPz/16-assignment-1-submission
Total Hours: |  |  | 1
Week 5 (25th June 2018 – 1st July 2018)
Task | Type (Project or Coursework) | Supporting Documentation | Hours spent
Watch video chat, make relevant notes | Coursework |  | 1
Mentor meeting | Coursework |  | 0.5
Group Meeting | Coursework | https://github.com/LateJoiners/docs/commit/123938f313cf8564976d62395f023e37f6b1d653 | 0.5
Angular CLI Tutorials | Project | https://trello.com/c/mcKUmMWh | 2
Assignment 2 commencement | Coursework | https://trello.com/c/v4crUofR | 1
Github commits for Week | Project | https://github.com/LateJoiners/docs/commits?author=matty-g&since=2018-06-28T14:00:00Z&until=2018-06-29T14:00:00Z
Total Hours: |  |  | 5
Week 6 (2nd July 2018 - 8th July 2018)
Task | Type (Project or Coursework) | Supporting Documentation | Hours spent
Watch video chat, make relevant notes | Coursework |  | 1
Mentor meeting | Coursework |  | 0.5
Group Meeting | Coursework | https://github.com/LateJoiners/docs/commit/3e64eda3bcaa910c14499f02bd820fe27e6cec0d | 0.75
API Research | Project | https://trello.com/c/sE7T0qWs | 1
A2 continuation | Coursework | https://trello.com/c/8IExsoHR | 1
Design Prototyping Research | Project | https://trello.com/c/OXwAuVyB | 1
Github Commits for week | Project | https://github.com/LateJoiners/docs/commits?author=matty-g&since=2018-07-03T14:00:00Z&until=2018-07-04T14:00:00Z
Total Hours: |  |  | 5.25
Week 7 (9th July 2018 - 15th July 2018)
Task | Type (Project or Coursework) | Supporting Documentation | Hours spent
Watch video chat, make relevant notes | Coursework |  | 1
Mentor meeting | Coursework | https://rmitlatejoiners.slack.com/archives/CBEERJYPR/p1531218783000009 | 0.5
Group Meeting | Coursework | https://trello.com/c/TrvxvxBO | 0.5
A2 Prototyping | Coursework | https://trello.com/c/uYFiC4PN | 1.5
Bootstrap Tutorials | Project | https://trello.com/c/8Nv1ypBL | 2
Github Commits | Project | https://github.com/LateJoiners/docs/commits?author=matty-g&since=2018-07-19T14:00:00Z&until=2018-07-21T14:00:00Z
Total Hours: |  |  | 5.5
Week 8 (16th July 2018 - 22nd July 2018)
Task | Type (Project or Coursework) | Supporting Documentation | Hours spent
Watch video chat, make relevant notes | Coursework |  | 1
Group Meeting | Coursework | https://trello.com/c/j7RVoRqX | 1
Second Group Meeting | Coursework | https://trello.com/c/z8YJGKwT | 1
Estimations and Justifications for Assignment 2 | Coursework | https://github.com/LateJoiners/docs/commit/48720fc94c20a33ef0cd24225ec677fe83fa7543 | 0.5
Mockups for Assignment 2 | Project | https://github.com/LateJoiners/docs/commit/72a20f640bec4365818f616ddf87835463f2bc58 | 4
Total Hours: |  |  | 7.5
Week 9 (23rd July 2018 - 29th July 2018)
Task | Type (Project or Coursework) | Supporting Documentation | Hours spent
Watch video chat, make relevant notes | Coursework |  | 1
Team Evaluation 1 | Coursework
Group Meeting | Coursework | https://trello.com/c/qI56jS2b | 0.5
Additional Bootstrap dev | Project | https://trello.com/c/OdUYQdQG | 1.5
Total Hours: |  |  | 3
Week 10 (30th July 2018 - 5th August 2018)
Task | Type (Project or Coursework) | Supporting Documentation | Hours spent
Watch video chat, make relevant notes | Coursework |  | 1
Group Meeting | Coursework | https://rmitlatejoiners.slack.com/archives/CB1L87SRG/p1533117622000218 | 1
Mentor meeting | Coursework | https://trello.com/c/zFQ5vYRf | 0.5
A3 commencement | Coursework | https://trello.com/c/XtpJX4m2 | 1.5
Github Commits for week | Project | https://github.com/LateJoiners/docs/commits?author=matty-g&since=2018-08-04T14:00:00Z&until=2018-08-05T14:00:00Z
Total Hours: |  |  | 4
Week 11 (6th August 2018 – 12th August 2018)
Task | Type (Project or Coursework) | Supporting Documentation | Hours spent
Watch video chat, make relevant notes | Coursework |  | 1
Group Meeting | Coursework | https://rmitlatejoiners.slack.com/archives/CB1L87SRG/p1533722504000013 | 1
Mentor meeting | Coursework | https://trello.com/c/RQYXKaMy | 0.5
A3 progression | Coursework | https://trello.com/c/dLZT6YCH | 3
Github Commits for week | Project | https://github.com/LateJoiners/docs/commits?author=matty-g&since=2018-08-12T14:00:00Z&until=2018-08-18T14:00:00Z
Total Hours: |  |  | 5.5
Week 12 (13th August 2018 - 19th August 2018)
Task | Type (Project or Coursework) | Supporting Documentation | Hours spent
Watch video chat, make relevant notes | Coursework |  | 1
Mentor meeting | Coursework | https://rmitlatejoiners.slack.com/archives/CB1L87SRG/p1534242781000100 | 0.5
Assignment 3 Part 1 | Coursework | https://github.com/LateJoiners/docs/commit/4daff0d19dc6b735c3e7a5404ac083ff7a1d41d1 https://trello.com/c/3wLyrDyV/20-assignment-3-submission | 8
Mock Data creation | Project | https://github.com/LateJoiners/code/commit/8319fa91dc8ae5dbb94f0d0905764cc8cc9345d7#diff-e8e998d8520f7dca190948da806175c5 | 2
Group Catchup | Coursework | https://rmitlatejoiners.slack.com/archives/CB1L87SRG/p1534327299000100 | 0.5
Total Hours: |  |  | 12
Week 13 (20th August 2018 - 26th August 2018)
Task | Type (Project or Coursework) | Support Documentation | Hours spent
Complete this document | Coursework | You’re looking at it | 1
Ladder component | Project | https://github.com/LateJoiners/code/commit/be383ccc253f0b526dbc28dc85c13a5b593fd013 | 3
Round/tip entering component | Project | https://github.com/LateJoiners/code/commit/6362a48efa0dede961cb7536706bb195afa58660 | 10
League Component | Project | https://github.com/LateJoiners/code/commit/b083a29692874e02748f8bb898cf426ad0bf3160 | 4
A3 Pt. 2 Video | Project |  | 8
Total Hours: |  |  | 26
Total Study Period Coursework Hours: | 36.25 | Total Study Period Project Hours: | 38.5
Total Study Period Hours: |  |  | 74.75